## Summary
Application Name
Client Company Name: | xxx
Client Contact Name: | xxx
Estimated By: | Claudiu Cretu
Estimated Date: | 2011-02-01
| Hours | Man Days | Hourly Cost | Cost
Development Effort | 192 | 24 | 1 | 192
System Testing Effort | 39 | 4.875 | 1 | 39
Project Management | 24 | 3 | 1 | 24
Development buffer&Bugfixing | 25.5 | 3.1875 | 1 | 25.5
Totals Cost | 255 |  |  | 255

## Estimation
# | Module | Feature / Task | Man hours | Comments
| Project startup | Meeting, requirements clarification, set up the project | 16
1 | Diagnosis & Treatment | Treatment Page - Create layout to display the informations needed, create table in DB and implement CRUD functionality. | 16 | done
2 |  | Diagnosis Page - Create layout to display the informations needed, create table in DB and implement CRUD functionality. | 16 | done
5 | Messages (SMS) | From drug store or dispensary - validate the message, if it is correct then process and save it in DB. | 24
6 |  | To drug store or dispensary - create, save and send the message | 24
7 |  | Message Page - Create layout to display the messages that the application receives from drug store and from dispensary, create table in DB and implement the functionality. | 16
8 | Email | Create and send the email, save email in DB | 16
9 | Reports | Drug Shop Report - Create layout, charts, implement the functionality needed to display the data. | 32
10 |  | Dispensary Report - Create layout, charts, implement the functionality needed to display the data. | 32
|  | Development Effort | 192

## Questions
Question # | Section | Clear? | Question | Answer
1 | Project startup
2 | Diagnosis & Treatment
4 | Errors | No | What should be consider an error?
5 | Messages (SMS)
6 | Email
7 | Reports | No | What type of charts do you whant in the reports? (pie, bar etc.)
|  | No | What information should apear in the charts?